## Overview
Videoconf App — Progress Snapshot
Generated by scripts/build_progress_xlsx.py
Total fitur sudah dibuat | 112
Total gap (belum dibuat) | 116
Persentase progress (kasar, by jumlah item) | 49%
Breakdown sudah dibuat per kategori
Kategori | Jumlah | Persen total done
Frontend | 61 | 54%
Backend | 42 | 38%
Infra | 6 | 5%
Docs | 3 | 3%
Sisa gap by effort estimate
Effort | Jumlah | Catatan
S | 62 | Small (<2 jam)
M | 36 | Medium (~setengah hari sampai 1 hari)
L | 17 | Large (>1 hari, multi-session)
— | 1 | Belum di-scope / butuh keputusan dulu

## Sudah Dibuat
Kategori | Sprint / Tahap | Fitur | Bagian | File path utama | Catatan
Infra | Sprint 1 | Docker Compose: LiveKit + MySQL + Redis | Infra | docker-compose.yml | Awal project
Backend | Sprint 1 | Go module + struktur internal/ | Backend | backend/go.mod | Gin + middleware skeleton
Backend | Sprint 1 | Config loader (.env via godotenv) | Backend | backend/internal/config/config.go
Backend | Sprint 1 | CORS middleware (dev permissive, prod env-driven) | Backend | backend/internal/middleware/cors.go | AllowOriginFunc di dev
Backend | Sprint 1 | GET /api/health endpoint | Backend | backend/cmd/server/main.go
Backend | Sprint 1 | POST /api/token (LiveKit JWT generation) | Backend | backend/internal/handlers/token.go | Pakai livekit/protocol/auth
Backend | Sprint 2 | Migration 001: users + rooms tables | Backend | db/migrations/001_init.sql
Backend | Sprint 2 | MySQL connection (database/sql + pool tuning) | Backend | backend/internal/db/db.go | MaxOpenConns=25
Backend | Sprint 2 | User model + UserRepo (Create, GetByID, GetByEmail) | Backend | backend/internal/repo/user_repo.go
Backend | Sprint 2 | App JWT helper (golang-jwt/v5) | Backend | backend/internal/auth/jwt.go | HS256, 24h TTL
Backend | Sprint 2 | RequireAuth middleware (Bearer token) | Backend | backend/internal/middleware/auth.go
Backend | Sprint 2 | POST /api/auth/register (bcrypt hash) | Backend | backend/internal/handlers/auth.go
Backend | Sprint 2 | POST /api/auth/login | Backend | backend/internal/handlers/auth.go
Backend | Sprint 2 | Rate limit middleware (token bucket per IP) | Backend | backend/internal/middleware/ratelimit.go | 5 burst/min — di /auth endpoints
Backend | Sprint 3 | Room model + RoomRepo (CRUD) | Backend | backend/internal/repo/room_repo.go
Backend | Sprint 3 | POST /api/rooms (create) | Backend | backend/internal/handlers/rooms.go
Backend | Sprint 3 | GET /api/rooms/my (list owned) | Backend | backend/internal/handlers/rooms.go
Backend | Sprint 3 | GET /api/rooms/:idOrSlug (detail) | Backend | backend/internal/handlers/rooms.go
Backend | Sprint 3 | DELETE /api/rooms/:idOrSlug | Backend | backend/internal/handlers/rooms.go | Owner only, cascading delete
Backend | Sprint 3 | Token endpoint access control (public/private/owner) | Backend | backend/internal/handlers/token.go
Backend | Sprint 4 | Migration 002: messages table (chat history) | Backend | db/migrations/002_messages.sql
Backend | Sprint 4 | Migration 003: is_locked column | Backend | db/migrations/003_room_lock.sql
Backend | Sprint 4 | Migration 004: recordings table | Backend | db/migrations/004_recordings.sql
Backend | Sprint 4 | MessageRepo + chat endpoints (POST/GET messages) | Backend | backend/internal/handlers/chat.go | Cursor pagination via 'before'
Backend | Sprint 4 | Host controls: lock/unlock room | Backend | backend/internal/handlers/participants.go | API only
Backend | Sprint 4 | Host controls: list/mute/kick participants | Backend | backend/internal/handlers/participants.go | Pakai LiveKit RoomService
Backend | Sprint 4 | LiveKit RoomService client wrapper | Backend | backend/internal/livekit/client.go
Backend | Sprint 4 | LiveKit Egress client wrapper | Backend | backend/internal/livekit/egress.go
Backend | Sprint 4 | Recording API (start/stop/list/get) | Backend | backend/internal/handlers/recordings.go | S3 storage config dependent
Infra | Sprint 4 | MinIO + Egress container di docker-compose | Infra | docker-compose.yml + config/
Infra | Sprint 4 | LiveKit config YAML (non-dev, Redis-enabled) | Infra | config/livekit.yaml
Backend | Polish | Gin release mode via APP_ENV=production | Backend | backend/cmd/server/main.go
Backend | Polish | Graceful shutdown (SIGINT/SIGTERM + ctx timeout) | Backend | backend/cmd/server/main.go
Docs | Polish | API reference Markdown | Docs | backend/API.md | Lengkap dengan request/response + error codes
Docs | Polish | Swagger UI di /swagger/index.html | Docs | backend/docs/ | swaggo/gin-swagger; dev only
Docs | Polish | Swag annotations di semua handler | Docs | backend/internal/handlers/*.go | swag init regen ulang
Backend | Guest | POST /rooms/:slug/guest-token (no auth) | Backend | backend/internal/handlers/token.go | Random guest identity
Backend | Guest | Room route public (di luar ProtectedRoute) | Frontend | frontend/src/App.tsx
Frontend | FE Hari 1 | Vite + React 19 + TypeScript scaffold | Frontend | frontend/vite.config.ts
Frontend | FE Hari 1 | Tailwind v4 (config-less via plugin) | Frontend | frontend/src/index.css | @import 'tailwindcss'
Frontend | FE Hari 1 | React Router v7 + TanStack Query v5 | Frontend | frontend/src/App.tsx + main.tsx
Frontend | FE Hari 1 | Path alias @/* (vite + tsconfig) | Frontend | frontend/vite.config.ts
Frontend | FE Hari 1 | Folder structure (pages/components/lib/hooks) | Frontend | frontend/src/
Frontend | FE Hari 1 | Env config (VITE_API_BASE_URL) | Frontend | frontend/.env
Frontend | FE Hari 1 | API wrapper + JWT in localStorage | Frontend | frontend/src/lib/api.ts | ApiError class + code field
Frontend | FE Hari 1 | useAuth hook (token state) | Frontend | frontend/src/hooks/useAuth.ts
Frontend | FE Hari 1 | Routing skeleton 7 routes + ProtectedRoute + NotFound | Frontend | frontend/src/App.tsx
Frontend | FE Hari 2 | Custom theme: zinc warm + orange flame | Frontend | frontend/src/index.css | @theme di Tailwind v4
Frontend | FE Hari 2 | Plus Jakarta Sans + JetBrains Mono fonts | Frontend | frontend/src/index.css | @fontsource-variable
Frontend | FE Hari 2 | Form primitives: Button, Field, Input, PasswordInput, Alert | Frontend | frontend/src/components/ui/
Frontend | FE Hari 2 | Layout (header + WIB clock + footer) | Frontend | frontend/src/components/Layout.tsx
Frontend | FE Hari 2 | AuthLayout (split layout) | Frontend | frontend/src/components/AuthLayout.tsx
Frontend | FE Hari 2 | Login page (react-hook-form + zod + API) | Frontend | frontend/src/pages/Login.tsx
Frontend | FE Hari 2 | Register page | Frontend | frontend/src/pages/Register.tsx
Frontend | FE Hari 2 | Home/landing page (asymmetric + mock meeting card) | Frontend | frontend/src/pages/Home.tsx
Frontend | FE Hari 2 | Film-grain noise overlay + warm focus ring | Frontend | frontend/src/index.css | UI/UX human, anti-AI generic
Frontend | FE Hari 3 | useRooms hook (TanStack Query list/create/delete) | Frontend | frontend/src/hooks/useRooms.ts
Frontend | FE Hari 3 | Badge + Dialog primitive components | Frontend | frontend/src/components/ui/
Frontend | FE Hari 3 | CreateRoomDialog (name + slug + public toggle) | Frontend | frontend/src/components/CreateRoomDialog.tsx
Frontend | FE Hari 3 | copyText clipboard helper (fallback legacy) | Frontend | frontend/src/lib/clipboard.ts
Frontend | FE Hari 3 | Dashboard: list/empty/skeleton/copy link/delete-confirm | Frontend | frontend/src/pages/Dashboard.tsx
Frontend | FE Hari 4 | Install @livekit/components-react + livekit-client | Frontend | frontend/package.json | Auto code-split via React.lazy
Frontend | FE Hari 4 | useRoomToken hook (POST /api/token) | Frontend | frontend/src/hooks/useRoomToken.ts
Frontend | FE Hari 4 | Lobby page (input slug → navigate) | Frontend | frontend/src/pages/Lobby.tsx | Auto-extract slug dari URL lengkap
Frontend | FE Hari 4 | Room page dengan phase state machine | Frontend | frontend/src/pages/Room.tsx | prejoin → connecting → joined → disconnected
Frontend | FE Hari 4 | Pre-join screen (mic/cam toggle) | Frontend | frontend/src/pages/Room.tsx
Frontend | FE Hari 4 | Error mapping (404/403/401) dengan copy Indonesia | Frontend | frontend/src/pages/Room.tsx
Frontend | FE Hari 4 | <LiveKitRoom> + <VideoConference> integration | Frontend | frontend/src/pages/Room.tsx | Code-split chunk ~600kb
Frontend | Guest | Pre-join username field untuk guest | Frontend | frontend/src/pages/Room.tsx | Persist ke localStorage
Frontend | Guest | useRoomToken support guest mode | Frontend | frontend/src/hooks/useRoomToken.ts
Frontend | Polish | ChatToastNotifier (bottom-right fade in/out) | Frontend | frontend/src/components/ChatToastNotifier.tsx | Pakai useChat LiveKit
Frontend | Polish | Disconnect → 'Sambung lagi' UI (gak auto-navigate) | Frontend | frontend/src/pages/Room.tsx | DisconnectedState component
Frontend | Polish | Auto-rejoin exponential backoff (3 retries: 1.5s/3s/6s) | Frontend | frontend/src/pages/Room.tsx | Skip terminal reasons
Frontend | Recording | useRoomInfo hook (room detail + isOwner) | Frontend | frontend/src/hooks/useRoomInfo.ts
Frontend | Recording | getCurrentUserId helper (JWT decode payload) | Frontend | frontend/src/lib/api.ts
Frontend | Recording | RecordingIndicator (badge buat semua peserta) | Frontend | frontend/src/components/RecordingIndicator.tsx | Pakai useIsRecording LiveKit
Frontend | Recording | RecordingControl (owner only, start/stop) | Frontend | frontend/src/components/RecordingControl.tsx | Auto-recover activeId via list endpoint
Frontend | Host UI | RoomControls (floating toolbar top-left) | Frontend | frontend/src/components/RoomControls.tsx
Frontend | Host UI | ParticipantsPanel (slide-in dari kiri + mute/kick) | Frontend | frontend/src/components/ParticipantsPanel.tsx | Owner only
Frontend | Engage | Reactions (8 emoji picker via data channel) | Frontend | frontend/src/components/Reactions.tsx | Topic 'vc.reaction'
Frontend | Engage | Floating emoji animation (CSS keyframe) | Frontend | frontend/src/index.css | .reaction-float, 2.8s
Frontend | Engage | RaiseHandButton (toggle via participant.setAttributes) | Frontend | frontend/src/components/RaiseHandButton.tsx
Frontend | Engage | ParticipantsPanel ✋ indicator + sort + counter badge | Frontend | frontend/src/components/ParticipantsPanel.tsx
Frontend | Engage | Web Audio API sound helpers (join/leave/chat/reaction) | Frontend | frontend/src/lib/sounds.ts | No asset files, mute toggle localStorage
Frontend | Engage | RoomEventSounds (LiveKit event → play) | Frontend | frontend/src/components/RoomEventSounds.tsx
Infra | Deploy | Vite preview production build (no HMR) | Infra | frontend/vite.config.ts | Production-stable buat testing live
Infra | Deploy | cloudflared free tunnel buat URL HTTPS publik | Infra | (runtime) | URL ganti tiap restart
Infra | Deploy | LiveKit Cloud integration (free tier) | Infra | backend/.env | Ganti 3 env doang, code provider-agnostic
Backend | Sched | Migration 005: scheduled_at + duration_minutes | Backend | db/migrations/005_room_schedule.sql
Backend | Sched | CreateRoom accept scheduled_at + duration | Backend | backend/internal/handlers/rooms.go | Validation 5-480 min
Frontend | Sched | schedule.ts helpers (format + relative) | Frontend | frontend/src/lib/schedule.ts | scheduleRelative dengan upcoming/live/past
Frontend | Sched | CreateRoomDialog toggle 'Dijadwalkan' + datetime + durasi | Frontend | frontend/src/components/CreateRoomDialog.tsx
Frontend | Sched | Dashboard schedule display + sort + auto-refresh 30s | Frontend | frontend/src/pages/Dashboard.tsx
Frontend | Sched | Schedule badge (terjadwal/live/selesai) | Frontend | frontend/src/pages/Dashboard.tsx
Backend | Password | Migration 006: password_hash column | Backend | db/migrations/006_room_password.sql | bcrypt
Backend | Password | Token + GuestToken cek password (owner bypass) | Backend | backend/internal/handlers/token.go | Error code password_required/invalid
Frontend | Password | ApiError.code field | Frontend | frontend/src/lib/api.ts
Frontend | Password | CreateRoomDialog field password | Frontend | frontend/src/components/CreateRoomDialog.tsx
Frontend | Password | Pre-join auto-prompt password (saat password_required) | Frontend | frontend/src/pages/Room.tsx
Frontend | Password | Dashboard badge 🔒 password | Frontend | frontend/src/pages/Dashboard.tsx
Frontend | Invite | lib/invite.ts (.ics generator RFC 5545 + mailto) | Frontend | frontend/src/lib/invite.ts | Pure client, no SMTP
Frontend | Invite | Dashboard Share menu (Copy/Calendar/Email) | Frontend | frontend/src/pages/Dashboard.tsx
Backend | Recurring | Migration 007: recurrence column | Backend | db/migrations/007_room_recurrence.sql | daily/weekly
Backend | Recurring | CreateRoom validate recurrence (requires scheduled_at) | Backend | backend/internal/handlers/rooms.go
Frontend | Recurring | nextOccurrence + recurrenceLabel helpers | Frontend | frontend/src/lib/schedule.ts
Frontend | Recurring | Dialog dropdown 'Pengulangan' | Frontend | frontend/src/components/CreateRoomDialog.tsx
Frontend | Recurring | Dashboard 🔁 + 'Setiap Senin · 14.00' | Frontend | frontend/src/pages/Dashboard.tsx
Frontend | Recurring | Sort by next occurrence (always 'upcoming') | Frontend | frontend/src/pages/Dashboard.tsx
Backend | Waiting | Migration 008: waiting_room_enabled + waiting_requests | Backend | db/migrations/008_waiting_room.sql | ⚠️ IN PROGRESS
Backend | Waiting | WaitingRequest model | Backend | backend/internal/models/waiting.go | ⚠️ IN PROGRESS
Backend | Waiting | WaitingRepo (Create/GetByToken/ListPending/Approve/Deny) | Backend | backend/internal/repo/waiting_repo.go | ⚠️ IN PROGRESS
Backend | Waiting | Room.WaitingRoomEnabled field + repo update | Backend | backend/internal/models/room.go + repo | ⚠️ IN PROGRESS

## Belum Dibuat
Section | Fitur | Effort | Catatan
01. Sebelum meeting | Waiting room (sisanya: handlers + token integration + frontend UI) | M | Sebagian backend udah; sisa: tokenResponse pakai status field, handler status/list/admit/deny/toggle, routes, frontend hooks + Room phase + WaitingRoomPanel + dialog toggle
01. Sebelum meeting | Co-host designation | M | Tabel room_cohosts + 3 endpoint + permission helper diterapkan ke ~10 endpoint owner-gated (lock/mute/kick/recording)
01. Sebelum meeting | Send invitation email via SMTP | M | Sekarang mailto: client-only. Butuh SMTP service (Brevo/SES/Gmail App Pass) + worker
01. Sebelum meeting | Google Calendar / Outlook OAuth | L | Full OAuth flow + token storage + event create API
02. Pre-join screen | Live camera preview | S | getUserMedia + <video> di pre-join
02. Pre-join screen | Mic level meter (visualisasi audio) | S | Web Audio AnalyserNode di stream
02. Pre-join screen | Device picker (camera/mic/speaker) | S | navigator.mediaDevices.enumerateDevices + select
02. Pre-join screen | Test audio (record-playback) | S | Sederhana: rekam ~3s, playback
02. Pre-join screen | Saved device preferences | S | localStorage
02. Pre-join screen | Background blur preview | M | LiveKit Track Processor
02. Pre-join screen | Virtual background preview | L | TensorFlow.js/MediaPipe segmentation
03. Tampilan & layout | Speaker view vs grid toggle | S | Ganti VideoConference layout prop
03. Tampilan & layout | Pin participant (untuk self) | S
03. Tampilan & layout | Spotlight (host pin ke semua) | M | Pakai room metadata
03. Tampilan & layout | Hide self view | S
03. Tampilan & layout | Picture-in-Picture browser | S | document.pictureInPictureElement
03. Tampilan & layout | Full-screen toggle button | S | requestFullscreen()
03. Tampilan & layout | Timer durasi meeting di corner | S
03. Tampilan & layout | Connection quality indicator per participant | S | LiveKit Participant.connectionQuality
03. Tampilan & layout | Floating self-view drag | M
04. Audio | Push-to-talk (tahan spasi) | S
04. Audio | 'Kamu di-mute tapi sedang bicara' warning | S | VAD via Web Audio
04. Audio | Audio-only mode (matiin video) | S
04. Audio | Noise suppression toggle | M | LiveKit Cloud support
04. Audio | Music mode | S
04. Audio | Live transcription / captions | L | Whisper API atau LiveKit AI agent
05. Video | Mirror video / flip | S
05. Video | HD video toggle | S | LiveKit publishOptions
05. Video | Avatar di tile kalo cam off (selain inisial) | S
05. Video | Profile picture upload + display | M | Storage S3 + UI dialog
05. Video | Background blur | M
05. Video | Virtual background | L
05. Video | Beauty filter / AR effects | L
06. Screen share | Share with audio (Chrome tab) | S | getDisplayMedia({audio:true})
06. Screen share | Stop participant's share (host) | S | Pakai mute API
06. Screen share | Allow/disallow share (room setting) | S | Tambah field permission di token
06. Screen share | Laser pointer | S | Cursor overlay synced via data channel
06. Screen share | Annotation tools (gambar di screen) | M | Canvas overlay + sync
06. Screen share | Whiteboard collaborative | L | Canvas yang shared via data channel
07. Chat | Pakai chat history persistent kita (sync ke backend) | M | Sekarang LiveKit data channel doang, gak ke DB
07. Chat | Private 1-on-1 chat | M | Tambah recipient_id, ubah UI
07. Chat | @mention dengan notification | S
07. Chat | Emoji picker di input | S
07. Chat | Edit / delete pesan sendiri | S | Backend endpoint + UI
07. Chat | Reactions ke pesan (like, dll) | S
07. Chat | Reply / thread | M
07. Chat | File / image attachment | M | Storage S3 + UI uploader
08. Recording | Banner consent 'Meeting direkam' menonjol | S
08. Recording | Download link recording setelah selesai | S | Tergantung S3
08. Recording | Storage S3 setup di LiveKit Cloud | M | Konfigurasi external (bukan code)
08. Recording | Pilih layout recording (grid/speaker/share) | S | Param Egress request
08. Recording | Pause/resume | M | LiveKit Egress API
08. Recording | Auto-transcribe | L
09. Host controls | Lock room toggle di toolbar (UI) | S | API udah ada
09. Host controls | Mute all participants sekaligus | S | Loop ke semua + call mute API
09. Host controls | Lower all hands sekaligus | S
09. Host controls | Allow/disallow participants unmute themselves | M | Permission flag di room
09. Host controls | Disable chat (room setting) | S
09. Host controls | Disable rename | S
10. Participant | Yes/No quick reaction (beda dari emoji) | S
10. Participant | Profile picture/avatar untuk akun login | M | S3 upload + UI
10. Participant | Display name change on-the-fly | S | setName via LiveKit
11. Breakout rooms | Bikin sub-rooms breakout | L | Sub-room creation + assign
11. Breakout rooms | Auto / manual assign peserta | M
11. Breakout rooms | Broadcast pesan ke semua breakout | M
11. Breakout rooms | Recall everyone ke main room | M
12. Polls / Q&A | Live polling (host kasih, peserta vote) | M | Tabel polls + votes + UI
12. Polls / Q&A | Q&A panel terstruktur | M
12. Polls / Q&A | Quiz mode | L
12. Polls / Q&A | Whiteboard interaktif | L
13. Connection | Bandwidth/quality indicator (RTT/jitter/loss) | S | LiveKit Room.engine stats
13. Connection | Manual quality switch (Auto/Low/Med/High) | S | publishOptions per quality
13. Connection | Reconnect status banner enhanced | S | Lebih informatif
13. Connection | Show statistics debug panel | S
13. Connection | Network change detection (pindah WiFi) | S
14. Mobile | Capacitor wrap (APK/IPA) | M | Per rencana awal — perlu DNS + cert
14. Mobile | Push notification incoming meeting | L | FCM/APNs + SDK
14. Mobile | Background audio mode (lock screen) | S
14. Mobile | Wake lock (layar tidak mati) | S | Wake Lock API
14. Mobile | PSTN dial-in (telpon biasa) | L | LiveKit SIP / vendor (Twilio)
15. Accessibility | Closed captions / live captions | L | Whisper/STT integration
15. Accessibility | Live transcription panel | L
15. Accessibility | Keyboard shortcuts (mute/cam/leave) | S
15. Accessibility | Shortcut cheat sheet (tekan '?') | S
15. Accessibility | High contrast theme | S
15. Accessibility | Light mode toggle | S | Sekarang dark only
16. Notifications | Sound mute toggle button (UI) | S | Logic ada di lib/sounds.ts
16. Notifications | Browser notification kalo tab background | S | Notification API
16. Notifications | 'Yakin keluar?' confirmation sebelum disconnect | S
16. Notifications | Granular toggle per sound type (di settings) | S
17. Security | End-to-end encryption (E2EE) | L | LiveKit support — config + key exchange
17. Security | Watermark di shared screen | M | Canvas overlay
17. Security | Disable copy chat | S | user-select:none + JS
17. Security | Required login domain (mis. @piko.co.id) | S | Cek di register/login
18. Admin | Meeting attendance report | M | Log participants per session
18. Admin | Meeting duration / quality stats | M
18. Admin | Admin dashboard org-level | L
18. Admin | Audit log host actions | S
18. Admin | Usage chart sederhana | S
19. UX touches | Settings dialog modal (sentral preferences) | M | Pintu masuk ke banyak settings
19. UX touches | Tooltip di tiap tombol | S
19. UX touches | First-time tour / onboarding | M | Joyride atau custom
19. UX touches | Permission denied helper (kasih cara fix) | S
19. UX touches | Default mute on join setting per user | S | localStorage
19. UX touches | Profile photo upload buat akun | M | S3
19. UX touches | Language selector (id/en) | M | i18next setup
19. UX touches | Show waktu lokal masing-masing peserta | S
S5. Fitur pembeda | Belum decide fitur diferensiator | — | Per xlsx: pilih 1-2 dari Waiting Room / AI Transcription / Breakout / Polling / Meeting Summary / Whiteboard
S6. Deploy | Deploy ke server beneran (VPS atau piko shared) | L | Sprint 6 territory
S6. Deploy | Production domain + HTTPS (Caddy/Let's Encrypt) | M
S6. Deploy | Self-host LiveKit (atau LiveKit Cloud paid tier) | M | Tinggal flip 3 env
S6. Deploy | Monitoring (Sentry + Uptime Kuma) | M
S6. Deploy | TURN server config (buat NAT traversal) | M | LiveKit built-in TURN
S6. Deploy | Database hardening + backup automated | M
S6. Deploy | Production CORS allowlist (bukan permissive) | S | Tinggal env CORS_ORIGINS
S6. Deploy | Named cloudflared tunnel (URL stabil) | S | Butuh Cloudflare account

## Roadmap
Sprint / Tahap | Status | Ringkasan
Sprint 1 — Foundation | ✅ Selesai | Infra + backend health + LiveKit token + Frontend Hari 1-4 (auth, dashboard, video call basic)
Sprint 2 — Auth & DB | ✅ Selesai | Migrations, user CRUD, JWT, register/login, rate limit
Sprint 3 — Room Mgmt | ✅ Selesai | Rooms CRUD, access control, slug generation, dashboard UI
Sprint 4 — Meeting Lanjut | ✅ Sebagian besar selesai | Chat persist, host controls (API+UI), recording (API+UI, storage S3 belum disetup). UI: lock toggle belum
Sprint 5 — Fitur Pembeda | ⏳ Belum mulai | Sebagian fitur sebenarnya udah ada (reactions, raise hand) tapi belum decide fitur HERO diferensiator
Sprint 6 — Production Deploy | ⏳ Belum mulai | Server live, domain HTTPS, monitoring, TURN, hardening. Nunggu server Docker baru per info user
Capacitor mobile wrap | ⏳ Belum mulai | Setelah Sprint 6 atau pas web udah polished